## Summary
QA Testing Metrics Summary
Metric | Value
Total Checks (Загальна кількість перевірок у чек-листі) | 269
Executed Checks (Скільки перевірок фактично виконано) | 139
Execution Rate (%) (Відсоток виконаних перевірок) | 51.6%
Pass (Відсоток успішно пройдених перевірок) | 131
Fail (Кількість перевірок, де знайдено дефект) | 8
Blocked (Перевірки, які неможливо виконати) | 0
Pass Rate (%) (Відсоток успішно пройдених перевірок) | 94.2%
Defects Found (Загальна кількість знайдених багів) | 8
Fixed Defects (Скільки багів виправлено розробниками) | 5
Open Defects (Скільки багів залишаються відкритими) | 3

## Test Execution
Status | Count
Pass | 131
Fail | 8
Blocked | 0
Not Executed | 130

## Defects by Severity
Status | Count
Critical | 1
Major | 4
Minor | 3
Trivial | 0

## Defects by Module
Module | Defects
Login | 0
Registration | 0
Home Page | 3
Stories | 2
Travelers | 0
My Profile | 2
Confirmation | 1

## Coverage
Module | Status
Login | Partially Tested | 20%
Registration | Partially Tested | 20%
Home Page | Tested | 100%
Stories | Partially Tested | 80%
Travelers | Partially Tested | 80%
My Profile | Partially Tested | 50%
Confirmation | Tested | 100%